## layout
[7 empty] | Process Description |  |  | Loops / Updating
Parts
|  | #1 | #2 | #3 | #4 | #5
Counts |  | 37 | 61 | 54 | 47 | 63
1 | 1.1 | [5 empty] | Part selection
2 |  | 1 | 1 | 1 | 1 | 1 |  | 1.1.1 | Part application
3 |  | 1 | 1 | 1 | 1 | 1 |  | 1.1.2 | Review steps in other plants
4 |  | 1 | 1 | 1 | 1 | 1 |  | 1.1.3 | Part future target
5 |  | 1 | 1 | 1 | 1 | 1 |  | 1.1.4 | Decision for development
6 |  | 1 | 1 | 1 | 1 | 1 |  | 1.1.5 | Part effect. Of overall $/time | 8.1
7 |  | 1 | 1 | 1 | 1 | 1 |  | 1.1.6 | Risk Assignment to use devp Part
|  |  | 1 | 1 |  |  |  | 1.1.7 | Parts supply chain
8 |  | 1 | 1 | 1 | 1 | 1 |  | 1.1.8 | 3D Model complete system / detail
9 | 2.1 | [5 empty] | scope , original copy
10 |  | 1 | 1 | 1 | 1 | 1 |  | 2.1.1 | Sample Acceptance Criteria
11 |  | 1 | 1 | 1 | 1 | 1 |  | 2.1.2 | Sample testing Criteria
12 |  | 1 | 1 | 1 | 1 | 1 |  | 2.1.3 | Technology metrics
13 | 3.1 | [5 empty] | Scope development plans
14 |  | 1 | 1 | 1 | 1 | 1 |  | 3.1.1 | Cost balance / Target
15 |  | 1 | 1 | 1 | 1 | 1 |  | 3.1.2 | HBI quality or longer life
16 | 4.1 | [5 empty] | Part drawings |  |  | 5.1 | 8.1
17 |  |  | 1 |  |  | 1 |  | 4.1.1 | 3D scanning
18 |  |  | 1 | 1 |  | 1 |  | 4.1.2 | 3D model(s)
19 |  |  |  | 1 | 1 | 1 |  | 4.1.3 | Assembly drawings
20 |  | 1 | 1 | 1 | 1 | 1 |  | 4.1.4 | Parts Drawings
21 |  | 1 | 1 | 1 | 1 | 1 |  | 4.1.5 | Fabrication drawings
22 |  | 1 | 1 | 1 | 1 | 1 |  | 4.1.6 | process layout
23 | [5 empty] | 1 |  | 4.1.7 | Stresses Simulations
24 | 5.1 | [5 empty] | Part material study |  |  | 7.1
25 |  | 1 | 1 |  |  | 1 |  | 5.1.1 | Original material
26 |  | 1 | 1 | 1 | 1 | 1 |  | 5.1.2 | Local market replacement
27 |  | 1 | 1 | 1 | 1 | 1 |  | 5.1.3 | updating 4.1
28 |  | 1 | 1 | 1 | 1 | 1 |  | 5.1.4 | Initial demo and production Costs
29 |  | 1 | 1 | 1 |  | 1 |  | 5.1.5 | Initial saving and cash flow mang.
30 | 6.1 | [5 empty] | Part service study
31 |  | 1 | 1 | 1 |  | 1 |  | 6.1.1 | Part delivery time original
32 |  | 1 | 1 | 1 | 1 | 1 |  | 6.1.2 | Part Delivery time devep
33 |  |  | 1 |  | 1 | 1 |  | 6.1.3 | Temperatures
34 |  |  | 1 | 1 | 1 | 1 |  | 6.1.4 | Availability
35 |  |  | 1 | 1 | 1 | 1 |  | 6.1.5 | Production / Quality
36 |  | 1 | 1 | 1 | 1 | 1 |  | 6.1.6 | Saving time in dept.
37 | 7.1 | [5 empty] | Part surface study
38 |  | 1 | 1 | 1 | 1 | 1 |  | 7.1.1 | Hardness profile
39 |  |  | 1 | 1 |  | 1 |  | 7.1.2 | Hardness source
40 |  |  | 1 |  |  | 1 |  | 7.1.3 | Cross sections , micro hardness
41 |  |  | 1 |  | 1 | 1 |  | 7.1.4 | Layout technology
42 |  | 1 | 1 | 1 | 1 | 1 |  | 7.1.5 | Update cost 5.1
43 | 8.1 | [5 empty] | Application and Metallurgical review
44 |  |  | 1 | 1 | 1 |  |  | 8.1.1 | Same application in another tech.
45 |  | 1 | 1 | 1 |  | 1 |  | 8.1.2 | layout for develop plan 1.1.3 | 1.1
46 |  |  | 1 | 1 | 1 | 1 |  | 8.1.3 | failure Modes analysis
47 | [5 empty] | 1 |  | 8.1.3 | Micro structure upgrading 4.1
48 | 9.1 | [5 empty] | Final Assembly drawing
49 |  |  | 1 | 1 | 1 | 1 |  | 9.1.1
50 | 10.1 | 1 |  |  |  |  | Final Fabrication drawing
51 |  |  |  | 1 | 1 | 1 |  | 10.1.1
52 | 11.1 | [5 empty] | Raw Shape / material study ( Testing)
53 |  | 1 | 1 |  |  |  |  | 11.1.1 | Test with original material
54 |  | 1 | 1 | 1 | 1 | 1 |  | 11.1.2 | Test with selected material
55 | 12.1 | [5 empty] | Raw Shape / material study ( Production)
56 | [5 empty] | 1 |  | 12.2.1 | Casting Sand
57 |  |  | 1 |  |  |  |  | 12.2.2 | Casting Precision
58 |  | 1 |  | 1 |  |  |  | 12.2.3 | Rolled plates / rods / bars
59 | [7 empty] | 12.2.4 | Forging
60 |  |  |  | 1 | 1 |  |  | 12.2.5 | Rough machining
61 |  |  |  |  | 1 |  |  | 12.2.6 | Weldments
62 |  | 1 | 1 | 1 | 1 | 1 |  | 12.1.7 | QC
63 | 13.1 | [5 empty] | Fabrication methods ( welding , bending)
64 |  |  |  |  | 1 |  |  | 13.1.1 | Welding layout
65 |  |  |  |  | 1 |  |  | 13.1.2 | Welding sequence
66 |  |  |  |  | 1 |  |  | 13.1.3 | Welding procedures
67 |  |  |  |  | 1 |  |  | 13.1.4 | Heat treatment after/before
68 | [7 empty] | 13.1.5 | Bending profile
69 | [7 empty] | 13.1.6 | Stresses relief
70 |  |  |  |  | 1 |  |  | 13.1.7 | QC
71 | 14.1 | [5 empty] | Machining method
72 |  |  | 1 | 1 |  | 1 |  | 14.1.1 | Material removal to finish | 12.1
73 |  |  | 1 |  |  | 1 |  | 14.1.2 | Equipment / tools selection
74 |  |  | 1 |  |  | 1 |  | 14.1.3 | Cycle study(s)
75 | [5 empty] | 1 |  | 14.1.4 | machining after heat treatment / coating
76 |  |  | 1 |  |  | 1 |  | 14.1.5 | Machining of Test
77 |  | 1 | 1 | 1 |  | 1 |  | 14.1.6 | Machining of devep parts
78 |  | 1 | 1 | 1 | 1 | 1 |  | 14.1.7 | QC
79 |  | 1 | 1 | 1 | 1 | 1 |  | 14.1.8 | total Machining cost , confirmed
80 | 15.1 | [5 empty] | fixtures Design ( Testing)
81 | [7 empty] | 15.1.1
82 | 16.1 | [5 empty] | Fixture Design ( Production)
83 |  |  | 1 |  | 1 |  |  | 16.1.1 | weldments fixtures
84 |  | 1 | 1 | 1 | 1 | 1 |  | 16.1.2 | Machining fixtures
85 | [5 empty] | 1 |  | 16.2.3 | Heat treatment Fixtures
86 |  |  | 1 | 1 |  |  |  | 16.2.4 | Coating fixtures
87 | 17.1 | [5 empty] | Heat treatment before / after
88 | [7 empty] | 17.2.1 | Normalizing
89 | [5 empty] | 1 |  | 17.2.2 | Annealing
90 |  |  | 1 |  |  | 1 |  | 17.2.3 | Stresses relief
91 | [7 empty] | 17.2.4 | blanket treatment
92 |  |  | 1 |  | 1 | 1 |  | 17.2.5 | QC
93 | 18.1 | [5 empty] | Finishing
94 |  |  |  | 1 |  |  |  | 18.2.1 | Chroming / Grinding
95 |  |  |  | 1 |  |  |  | 18.2.2 | Grinding
96 | [7 empty] | 18.2.3 | Honing
97 | [5 empty] | 1 |  | 18.2.4 | sugar blasting
98 |  |  |  | 1 | 1 | 1 |  | 18.1.5 | QC
99 | 19.1 | [5 empty] | Assembly / welding
100 |  |  | 1 | 1 |  |  |  | 19.1.1 | QC parts / before
101 |  |  | 1 |  |  |  |  | 19.2.2 | Welding procedure
102 |  |  |  | 1 |  |  |  | 19.2.3 | Assembly Procedure
103 |  |  | 1 | 1 |  | 1 |  | 19.1.4 | QC Assembly / after
104 | 20.1 | [5 empty] | Surface treatment or Coating
105 | [5 empty] | 1 |  | 20.2.1 | Flame hardening
106 | [7 empty] | 20.2.2 | Laser Hardening
107 | [7 empty] | 20.2.3 | Overlaying
108 |  |  | 1 |  |  |  |  | 20.2.4 | Spraying
109 | [7 empty] | 20.2.5 | High speed spraying
110 |  |  | 1 |  |  | 1 |  | 20.1.6 | QC
111 |  | 1 |  | 1 | 1 | 1 |  | 20.1.7 | painting / anti rust
112 | 21.1 | [5 empty] | Testing , Function / pressure
113 |  |  |  | 1 |  |  |  | 12.2.1 | hydraulic oil pressure test
114 |  |  | 1 |  |  |  |  | 12.2.2 | Anti freeze Pressure test
115 | [7 empty] | 12.2.3 | Gas pressure test
116 | [7 empty] | 12.2.4 | Load test
117 |  | 1 | 1 | 1 |  | 1 |  | 12.1.5 | QC